DEPARTMENT OF PUBLIC WORKS & HIGHWAYS

REGIONAL OFFICE IX

Veterans Avenue Extension, Tetuan, Zamboanga City

TERMS OF REFERENCE

Consulting Services for the Conduct of Feasibility Study of the

Proposed Mangusu-Muti Diversion Road,

Zamboanga City

# INTRODUCTION

Mangusu is a coastal barangay located in the northeastern part of Zamboanga City, Region IX, with a population of 5,608 based on the 2020 Census. Covering an area of approximately 15.16 square kilometers, it is known for its fishing communities and agricultural lands cultivating rice, corn, and coconut. Situated along the Moro Gulf and forming part of the city’s 2nd Congressional District, Mangusu plays a vital role in linking rural barangays to the main trade and commercial centers of Zamboanga City.

Meanwhile, Muti is an inland barangay also situated in the northeastern corridor of the city, along the Maharlika Highway. With a population of 3,420 as of 2020, Muti is primarily agricultural, with rubber, coconut, and high-value crops forming the bulk of its local produce. Its location makes it a strategic connector between the upland areas and the coastal barangays of the district.

The two barangays—Mangusu and Muti—are currently connected by a combination of local roads and segments of the Maharlika Highway. However, increasing traffic volume along the national highway, particularly near populated areas, has resulted in congestion and slower travel times. This situation calls for the development of an alternative route to improve accessibility and ensure the efficient movement of goods and services.

In response to this need, the Department of Public Works and Highways (DPWH) Regional Office IX is proposing the construction of the 16.62-kilometer Mangusu–Muti Diversion Road. The diversion road is envisioned to provide a high-capacity alternate route, easing congestion along the existing highway, reducing travel time, and supporting the local and regional economy.

As an initial undertaking, this phase of the feasibility study will focus on the alignment survey of the entire 16.62-kilometer road stretch and a topographic survey covering 10.00 kilometers of the proposed alignment. These surveys will generate accurate geospatial and terrain data that will serve as foundational inputs for subsequent engineering, economic, and environmental analyses.

The proposed diversion road is expected to enhance connectivity across northeastern Zamboanga City, decongest critical road networks, and foster socio-economic development by improving transport efficiency and reducing logistical constraints.

# OBJECTIVES

The main objective of this engagement under the Terms of Reference (TOR) is to undertake an alignment survey covering the entire 16.62-kilometer stretch of the proposed Mangusu–Muti Diversion Road in Zamboanga City. This activity aims to determine the most viable and technically sound route based on terrain conditions, accessibility, land use, and potential environmental or social constraints. Additionally, a detailed topographic survey covering a 10.00-kilometer priority segment will also be conducted to gather accurate geospatial and elevation data that will serve as foundational input for the subsequent phases of the feasibility study and preliminary engineering design.

Specifically, this consulting service intends to achieve the following objectives:

  - Conduct an alignment survey along the entire 16.62-kilometer proposed corridor to determine the most viable horizontal alignment options considering terrain features, land use, accessibility, and other physical and environmental constraints;

  - Conduct a detailed topographic survey along the proposed 10.00-kilometer alignment to produce an accurate ground representation of the project site, including natural and man-made features, horizontal and vertical controls, and existing terrain conditions;

  - Generate plan and profile drawings of the surveyed alignment with sufficient detail to inform alignment optimization, geometric design, and preliminary engineering analysis;

  - Identify and map major topographic constraints and features, such as rivers, creeks, slopes, drainage paths, structures, and vegetation that may affect alignment selection or future construction;

  - Support the identification of environmentally and socially sensitive areas through terrain-based observations, to be validated in subsequent phases of the study;

  - Provide technical input to the alignment validation process, enabling the determination of the most suitable horizontal and vertical alignment options based on the actual terrain data collected;

  - Compile survey data in formats compatible with GIS and CAD software, ensuring it can be readily used for future detailed design, hydrological modeling, and road safety assessments;

  - Ensure survey activities comply with DPWH standards and specifications, particularly those outlined in the latest edition of the DPWH Survey Manual and related engineering design guidelines.

# SCOPE OF CONSULTING SERVICES

The scope of works of the Consultant under this TOR shall include, but not necessarily be limited to, the conduct of an alignment survey and a detailed topographic survey in support of the preliminary planning and technical validation of the proposed road alignment. The consulting services will include the following major activities:

  - Alignment Survey

    - Identify at least three (3) possible alignments and/or structural configuration considering among others, technical difficulties, connectivity to the existing national road network, investment requirement, impact on the environment and social aspect of the project; and

    - Present to the DPWH Regional Office IX, through the Planning and Design Division, the best alignment or structural configuration based on the appropriate and agreed selection method (multi-criteria analysis) for approval, using geographic information system (GIS) maps (referenced to WGS 84).

  - Topographical Survey

    - Undertake preliminary topographical survey along the selected alignment. The Consultant shall set out and establish reference points at appropriate locations as key control points of the survey. These points shall be used as benchmarks for identification and use during the subsequent engineering surveys. The levelling shall be tied to the existing government benchmarks in the area. (“Geo-tagging”);

    - Conduct profiling with cross-sections taken at fifty (50) meters interval, unless local conditions require cross-section at closer intervals so as to provide the necessary details for earthwork, quantity calculations with an accuracy of twenty percent (20%) of the final quantities. Profiles and cross-sections shall be determined plus one hundred (100) meters beyond construction limits;

    - Prepare topographic maps with contours at 50-meter interval and coordinates and vicinity plan. All survey plans shall be prepared on reproducible materials of high quality;

    - River/creek profile and river/creek cross sections shall be surveyed for 500 meters each upstream and downstream sides from the centerline of the bridge. Cross-sections shall be measured at 50-meter interval;

    - Conduct preliminary inventory for potential road slope disasters in the road section under study. The road slope disasters in the road shall be determined and classified as soil collapse, rock slope collapse, landslide, road slip, debris flow, river erosion and coastal erosion; and

    - Use of any advanced technology/methodology related to the activity (i.e. LiDar) is allowed, provided that implementation of the survey and data processing will be faster, safer and more efficient. The Consultant shall prepare the necessary data inputs and comprehensively provide all the information required in processing the data to clearly illustrate the output needed to evaluate the project.

# REPORTING

  - Final results will be presented to the Planning and Design Division of the Regional Office IX.

  - During the contract period, coordination meetings with the Zamboanga City 2nd District Engineering Office and Regional Office IX must be conducted to: (a) initiate agreements, (b) discuss the progress of the work and preliminary output; (c) make comments and suggestions on a timely basis; and (d) resolve problems and issues that may be encountered.

  - Further, aside from the specified scope of works mentioned above, the Consultant may propose additional works to enhance the study, provided it shall bear no additional cost to the Government. The scope of any additional proposed works by the Consultant shall be established within the first two (2) months of the study, subject to the approval of the Government.

# EXPECTED DELIVERABLES OF THE CONSULTING SERVICE

  - The Consultant shall report the progress of all activities in the course of the contract implementation. The Consultant shall submit the following but not limited to:

- Inception Report which shall contain the detailed work program for the undertaking, methodologies, dates of report submissions and schedule of activities proposed to meet the requirements set in this Terms of Reference. A total of three (3) copies of the report shall be submitted to the implementing office in two (2) weeks after the commencement of the consulting service.

- Progress Report. This report shall include status report, physical and financial as well as developments, issues, findings as of the report period. A total of three (3) copies of the report and electronic file (editable and in PDF) shall be submitted to the implementing office starting on the second month from the commencement of the consulting service and every two (2) months thereafter.

- DRAFT FINAL REPORT which shall contain the details of the consultant’s findings and recommendation based on the scope of work outlined in this Terms of Reference. The report shall summarize the undertaking fully describing the methods used, findings and the investment priorities. The report shall include all relevant information which support the conclusions in sufficient detail to enable calculations to be verified and allow re-calculation with modification of the key assumption without the need of supplementary data. A total of five (5) copies of the report shall be submitted to the implementing office at least two (2) weeks prior to contract expiration. The reports shall be submitted in soft-bound copy with title of the report written at the spine together with traceable e-copies of all analyses and simulations made.  The implementing Office shall issue to the Consultant a Suspension Order as a time consideration for the Implementing Office and related reviewing Offices to have ample time to transmit, circulate, review and consolidate all comments to the said reports. Once the reports are sent back to the Implementing Office, the Implementing Office shall issue a Resumption Order upon return of the report for correction and revision.

- FINAL REPORT which shall incorporate all appropriate revisions and clarifications on the Draft Final Report. A total of ten (10) copies of the report shall be submitted to the implementing office in printed and e-copy format together with all the requirements set forth in this TOR on or before the contract expiration. The Final Reports shall be submitted in soft-bound copy with title of the report written at the spine.

  - The major deliverables of the Study will be:

    - Overall Summary of Accomplishment Report

    - Plan and Profile with the Final alignment incorporated in the Topographic/Hydrographic Plans

    - Other data/documents to be submitted shall include but not limited to:

      - Geo-tagged Photographs

      - Raw and Processed Survey Data

      - Map of the alignment (including shape file format), plot in/convert to WGS 84

All outputs shall be complied in the following reports presented in legible manner and all in English language and shall be submitted to DPWH in three (3) copies. Electronic file formats (i.e. Microsoft Office, Adobe PDF, AutoCAD, transport model input and output files, etc.) of all reports and documents systematically organized in traceable and auditable formats shall be prepared in DVD and/or CD, 3 copies each.

All Draft Final Outputs shall be submitted at least two weeks prior to the contract expiration and be subjected to review and evaluation of the Implementing Office, PPD, ESSD, and other relevant offices as deemed necessary. The reviewing office shall review the draft reports for a maximum of two weeks, therefore, Final Reports are expected to be delivered not later than the contract expiration.

  - Payments to the consultant shall be made in accordance with the schedule contained in the table that follows. However, payments shall only be made on the basis of actual work accomplished referring to the deliverables set in Section 5.2.

| DELIVERABLE | PERCENTAGE FROM TOTAL COST |
| --- | --- |
| Inception Report | 15% |
| Progress Reports | 15% |
| Draft Final Report | 50% |
| - Topographic/Hydrographic Survey Plans |  |
| Final Report and Executive Summary | 20% |
| TOTAL | 100% |

# STUDY SCHEDULE

The Study shall be completed within a period of two (2) months, commencing from the date of receipt of the Notice to Proceed (NTP).

# HUMAN RESOURCE/ STAFF REQUIREMENT

The Consultants shall be composed of qualified staff with experience in the conduct of data gathering for infrastructure feasibility studies including preliminary design, traffic, social, and environmental impact assessment.

| KEY STAFF | Week |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| Senior Geodetic Engineer |  |  |  |  |  |  |  |  |

The Consultant shall provide the following key staff and the job description and required qualifications are prescribed below:

| Position | Job Description | Required Qualification | No. of Months |
| --- | --- | --- | --- |
| Senior Geodetic Engineer | Undertake topographic survey and provide the necessary topographic maps in aide of the preliminary design of alignment(s). | Bachelor's Degree in Geodetic/ Civil Engineering, with experience in the field of surveying. He/she must be familiar and adept with state-of-the-art technologies in surveying and research work with extensive experience in river survey (topographic, hydrographical and cross-sectional survey) and topographic/profile survey for urban drainage structures. | 1.0 |

# INSTITUTIONAL ARRANGEMENT

  - Implementing Office (DPWH Regional Office IX)

    - Disburse the fund for the conduct of the F/S once the contract is executed;

    - Implement and manage the contract, including ensuring the quality of output, the monitoring and evaluation of the progress of the study and approval of reports to ensure delivery of outputs as specified in this TOR;

    - Provide assistance in the coordination with other concerned agencies/entities in the conduct of the study;

    - Provide reasonable technical assistance to personnel of the Consultant with respect to incidents related to the conduct of the study;

    - Provide, upon the request of the Consultant, available information/data and also if available, copies of previous related studies subject to the execution of the Confidentiality and Non-Disclosure Agreement (CNDA), if necessary.

    - Coordinate with the Project Preparation Division – Planning Service of the DPWH regarding all the activities relating to the conduct of the study, included but not limited to the implementation timelines, submission of deliverables, notice of meetings, etc. Should the need arise, consult with the PPD-PS in the implementation of the study.

  - Planning Service – Central Office

    - Provide technical assistance to the Implementing Office

    - Be responsible for contract implementation and management, including ensuring the quality of output, the monitoring and evaluation of the progress of the study and approval of reports to ensure delivery of outputs as specified in this TOR;

  - Consultant

    - Conduct the study and deliver on time the results/outputs as indicated in this TOR;

    - Provide the necessary office equipment for the conduct of the study as specified under Annex A of the Approved Budget for the Contract (ABC). All equipment procured for the development of the project shall be transferred to the Government by the end of the project;

    - Shoulder all expenses required in the conduct of the study, including travel costs and lodging of detailed Government personnel during field visits, except for their salaries;

    - Carry out the services with sound engineering theories and practices to ensure that the final works will provide the most economical and feasible development for the study;

    - Accept full responsibility for the consulting services to be performed under this TOR for which the Consultant is liable to DPWH;

    - Perform the work in an efficient and diligent manner and shall use its best effort to keep reimbursable costs down to the possible minimum without impairing the quality of services rendered;

    - Comply with, and strictly observe any laws regarding workmen’s health and safety, workmen’s welfare, compensation for injuries, minimum wage, hours of labor and other labor laws;

    - Keep accurate and systematic records and accounts in respect of the services in such form and detail as is customary and sufficient to establish accurately that the costs and expenditures under this TOR have been duly incurred;

    - Permit the duly authorized representatives of the Government from time to time to inspect its records and accounts as well as to audit the same;

    - Not allowed to assign nor sub-contract any part of the professional engineering services under this TOR to any person or firm, except with prior written consent. The approval by the Government to the assignment of any part of said services or to the engagement by the Consultant of sub-contractors to perform any part of the same shall not relieve the Consultant of any obligations under this TOR;

    - During the term of the contract and after its termination, the Consultant and any entity affiliated with the Consultant, as well as any Sub-consultant and any entity affiliated with such Sub-consultant, shall be disqualified from providing goods, works, or consulting services for any project resulting from or closely related to the contract other than the services and any continuation thereof provided there is no current or future conflict;

    - Prohibit full-time foreign staff during his assignment under this TOR to engage, directly or indirectly, either in his name, or through the Consultant, in any business or professional activities in the Philippines other than the performance of his duties or assignment under this TOR;

    - Not allowed, at any time, to communicate to any person or entity any information disclosed to them for the purpose of this services, nor shall the Consultant make public any information as to the recommendations formulated in the course of or as a result of the services, except with prior consent;

    - Agree that nothing contained herein shall be construed as establishing or creating between the Government and the Consultant, the relationship of employer and employee or principal and agent, it being understood that the position of the Consultant and anyone else performing the services is that of an independent contractor;

    - Hold the Government free from any and all liabilities, suits, actions, demands, or damages arising from death or injuries to persons or properties, or any loss resulting from or caused by said personnel incident to or in connection with the services under this TOR. The Consultant shall agree to indemnify, protect and defend at its own expense the Government and its agents from and against all actions, claims and liabilities arising out of acts done by the Consultant or its staff in the performance of the services, including the use of, or violation of any copyrighted materials, patented invention, article or appliance; and

    - Provide on-the-job capacity building/technology transfer to the Government’s personnel detailed to the project.

# OWNERSHIP OF THE OUTPUTS/REPORTS/DOCUMENTS

All submitted outputs/reports/documents under this contract, including but not limited to tracings, as-built drawings, estimates, digital information, computer model and data, specifications, investigations and studies completed or partially completed, inspection logs, and photographs, shall be the property of DPWH and the use of these data for other purposes shall require written consent from the Department. Copyrights will be governed by existing laws, rules and regulations.

Prepared By:						Reviewed by:

AIRALYNE A. MOJICA				REYNILDA D. TAN

Engineer II						Chief, Planning Section

Submitted by:						Recommending Approval:

MICHAEL D. TORINO, MPA			SORAY’YAH M. IBRAHIM, CESO IV

Engineer IV		 				Assistant Regional Director

OIC-Chief, Planning and Design Division

Approved By:

CAYAMOMBAO D. DIA, CESO III

Regional Director

RO9.1/AMA/RDT/PS

Include only if the Regional Office is the Implementing Office

Include only if the RO or DEO is the Implementing Office. No need to include if the Central Office is the IO