## 1
BULACAN 2ND DISTRICT ENGINEERING OFFICE
FORM POW - 2015-01-00
PROGRAM OF WORK/BUDGET COST
Project Name |  |  |  | : | Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
[18 empty] | Net Length | : | (a) Road
(b) Bridge
Project ID |  |  |  | : | [15 empty] | (c) Others
Project Component ID |  |  |  | :
Project Location |  |  |  | : | 4th, 6th and Lone Congressional District of Bulacan | [12 empty] | Target Start Date |  | :
Work Location |  |  |  | : | [13 empty] | Total Project Duration |  | :
Appropriation |  |  |  | : | Php 10,000,000.00 | 2500000 | [11 empty] | No. of Pre-determined |  | :
Source of Fund |  |  |  | : | SR2025-02-006195 - 01101101 - Regular Agency Fund - General Fund - New General Appropriations - | [12 empty] | Unworkable Days |  | :
Specific Budgets of National Government Agencies
DESCRIPTION OF WORKS TO BE DONE | [8 empty] | QUANTITY |  | UNIT |  |  | AS SUBMITTED | [5 empty] | AS EVALUATED
[14 empty] | % TOTAL |  | TOTAL DIRECT COST |  |  |  | % TOTAL |  | TOTAL DIRECT COST
Part | A | : | Facilities for the Engineer
| B | : | Other General Requirements
| C | : | Earthworks
| D | : | Subbase and Base Course | [5 empty] | (PLS. SEE FORM POW-2015-01C-00)
| E | : | Surface Courses
| F | : | Bridge Construction
| G | : | Drainage and Slope Protection Structures
| H | : | Miscellaneous Structures | [10 empty] | 100% |  | 2361312 |  |  |  | 100% |  | 2361312
| J | : | Flood Control and Drainage
| I -A | : | Earthwork
| I -B | : | Bank and Slope Protection Works
|  |  | Total | [10 empty] | 100% |  | 2361312 |  |  |  | 100% |  | 2361312
EQUIPMENT : | [7 empty] | BREAKDOWN OF EXPENDITURES :
DESCRIPTION | [6 empty] | REQUIRED | [5 empty] | AS SUBMITTED |  | AS EVALUATED | [6 empty] | AS SUBMITTED | AS EVALUATED
[8 empty] | 1. | Labor | [7 empty] | A. | Total Direct Cost |  |  |  | 2361312 | 2361312
[8 empty] | 2. | Materials |  |  |  | 2361312 |  | 2361312 |  | B. | OCM and Profit |  |  |  | 0 | 0
[8 empty] | 3. | Rental of Equipment | [7 empty] | C. | Value Added Tax |  |  |  | 118065.6 | 118065.6
[8 empty] | 4. | Provisional Sum | [7 empty] | D. | Total Construction Cost |  |  |  | 2479377.6 | 2479377.6
[8 empty] | 5. | Daywork | [7 empty] | E. | Eng'g. & Administrative Overhead, % |  |  | 2% | 0 | 0
(PLS. SEE FORM POW-2015-01BC-00) | [7 empty] | 6. | OCM and Profit | [7 empty] | F. | RROW Acquisition |  |  |  | 0 | 0
[8 empty] | 7. | Value Added Tax |  |  |  | 118065.6 |  | 118065.6 |  | G. | Physical Reserved (Contingency) |  |  |  | 0 | 0
[8 empty] | 8. | Eng'g. & Administrative Overhead, % |  |  | 2%
[8 empty] | 9. | RROW Acquisition |  |  |  | 0 |  | 0
[8 empty] | 10. | Physical Reserved (Contingency) |  |  |  | 0 |  | 0
[8 empty] | 11. | TOTAL ESTIMATED COST |  |  |  | 2479377.6 |  | 2479377.6 |  | H. | TOTAL ESTIMATED COST |  |  |  | 2479377.6 | 2479377.6
2500000
20622.4
Preparation and Submission : | [9 empty] | Evaluation : | [5 empty] | Approval : | [7 empty] | 2479377.6
0
Prepared by: | [6 empty] | Checked/Submitted by: |  |  | Reviewed: | [5 empty] | Recommending Approval: |  |  |  |  | Approved:
JAN ARVIN H. CRUZ | [6 empty] | ARNEL C. GUBALLA |  |  | ROGACIANO H. NICOLAS | [5 empty] | ACE M. CAPER |  |  |  |  | GEORGE DC. SANTOS
Engineer II | [6 empty] | Chief,Maintenance Section |  |  | OIC, Construction Section | [5 empty] | OIC, Assistant District Engineer |  |  |  |  | District Engineer
EDGAR A. SARTO
Engineer III

## 2
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
0
FORM POW-2015-01C-00
DETAILED BREAKDOWN OF COMPONENT FOR EACH ITEM
ITEM NO. | DESCRIPTION |  | % | QTY | UNIT | DIRECT COST |  |  |  | TOTAL MARK-UP |  | 5% VAT | TOTAL COST
[6 empty] | MATERIAL | LABOR | EQUIPMENT | TOTAL | % | VALUE
PART H | MISCELLANEOUS
| Traffic Services | AS SUBMITTED | 0% | 1 | ls. | 0 |  |  | 0 |  |  | 0 | 0
|  | AS EVALUATED | 0% | 1 | ls. | 0 |  |  | 0 |  |  | 0 | 0
1.4
1.4
| Traffic Services | AS SUBMITTED | 100% | 1 | ls. | 2361312 |  |  | 2361312 |  |  | 118065.6 | 2479377.6
|  | AS EVALUATED | 100% | 1 | ls. | 2361312 |  |  | 2361312 |  |  | 118065.6 | 2479377.6
0
0
| TOTAL OF PART H | AS SUBMITTED | 100% |  |  | 2361312 |  |  | 2361312 |  |  | 118065.6 | 2479377.6
|  | AS EVALUATED | 100% |  |  | 2361312 |  |  | 2361312 |  |  | 118065.6 | 2479377.6 | 45920012.74
| GRAND TOTAL | AS SUBMITTED | 100% |  |  | 2361312 |  |  | 2361312 |  |  |  | 2479377.6
|  | AS EVALUATED | 100%
[15 empty] | ROGACIANO H. NICOLAS | ACE M. CAPER

## 3
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
0
FORM POW-2015-01A-00
ITEMIZED BREAKDOWN
ITEM NO. | DESCRIPTION | QUANTITY |  | UNIT | DIRECT COST |  |  |  | TOTAL UNIT COST |  | % DIRECT COST
[5 empty] | TOTAL |  | UNIT COST |  | (DIRECT ÷ INDIRECT) |  |  |  | 33
|  | AS SUBMITTED | AS EVALUATED |  | AS SUBMITTED | AS EVALUATED | AS SUBMITTED | AS EVALUATED | AS SUBMITTED | AS EVALUATED | AS SUBMITTED | AS EVALUATED
PART H | MISCELLANEOUS
| Traffic Services | 1 | 1 | ls. | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.4
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Traffic Services | 1 | 1 | ls. | 2361312 | 2361312 | 2361312 | 2361312 | 2479377.6 | 2479377.6 | 100% | 100%
| TOTAL OF PART H |  |  |  | 2361312 | 2361312 | 2361312 | 2361312 | 2479377.6 | 2479377.6 | 100% | 100%
PART H | #REF!
0
| TOTAL OF PART E |  |  |  | 0 | 0 |  |  |  |  | 0% | 0%
| GRAND TOTAL |  |  |  | 2361312 | 2361312 | 2361312 | 2361312 | 2479377.6 | 2479377.6 | 100% | 100%
[14 empty] | ROGACIANO H. NICOLAS | ACE M. CAPER

## 4 abc
BULACAN 2ND DISTRICT ENGINEERING OFFICE
FORM ABC-2015-02A-00
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
0
APPROVED BUDGET FOR THE CONTRACT
ITEM NO. | DESCRIPTION |  |  | QTY | UNIT | TOTAL DIRECT COST | TOTAL MARK-UP |  | 5% VAT | TOTAL INDIRECT COST | TOTAL COST | UNIT COST
[7 empty] | % | VALUE
PART E | SURFACE COURSES
#REF! | #REF! |  | AS SUBMITTED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | AS EVALUATED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  | AS SUBMITTED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
|  |  | AS EVALUATED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 180
#REF! | #REF! |  | AS SUBMITTED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | AS EVALUATED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOTAL OF PART E |  | AS SUBMITTED |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  |  | AS EVALUATED |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
PART H | #REF!
#REF! | #REF! |  | AS SUBMITTED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | AS EVALUATED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  | AS SUBMITTED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
|  |  | AS EVALUATED | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
| TOTAL OF PART E |  | AS SUBMITTED |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  |  | AS EVALUATED |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
| GRAND TOTAL |  | AS SUBMITTED |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
|  |  | AS EVALUATED |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF!
Preparation and Submission : |  |  | Evaluation : |  |  | Approval : | [7 empty] | 180
Prepared by: |  | Checked/Submitted by: | Reviewed: |  |  | Recommending Approval: |  |  | Approved:
0
0
RONNEL BRYAN A. DE LEON |  | ARNEL C. GUBALLA | EDGARDO C. PINGOL |  |  | GENE S. LEAÑO |  |  | GEORGE DC. SANTOS |  |  |  |  | 0
Engineer II |  | Engineer II | Chief,Maintenance Section |  |  | Assistant District Engineer |  |  | District Engineer |  |  |  |  | 0
Maintenance Section |  | Maintenance Section | Maintenance Section

## 5
0
[8 empty] | 1 | Payloader (1.50 cu.m.) | 1 | 0.38 | 1733
[8 empty] | 1 | Bar Cutter | 1 | 0.5 | 219.75
[8 empty] | 1 | Bar Bender | 1 | 0.5 | 351.5
[6 empty] | FORM POW-2015-01B-00 |  | 1 |  | 1 | 0.19 | 1733
MINIMUM EQUIPMENT REQUIREMENT | [7 empty] | 1 |  | 1 | 0.15 | 1212
No. | Equipment Description | Capacity | Number of Equipment | No. | Equipment Description | Capacity | Number of Equipment | 1 | Motorized Road Grader (140 hp). G710A | 1 | 1 | 172
[8 empty] | 1 | Vibratory Roller (10 m.t.), SD100DC | 1 | 1 | 91.25
1 | Cargo Truck/Delivery Truck (2-5 T) | 5 T | 1 | 23 |  |  |  | 1 | Water Truck (16000 L) | 1 | 0.1 | 2450
2 | Applicator Machine |  | 1 | 24 |  |  |  | 1 | Asphalt Distributor, 10 ft. wide (5 tons) | 1 | 1 | 3379
3 | Kneading Machine |  | 1 | 25 |  |  |  |  | Cargo Truck (9-10 mt.) | 1 | 16 | 1212 | 19392
4 |  |  |  | 26 |  |  |  |  | Water Truck (16000 L.) | 1 | 16 | 2450 | 39200
5 |  |  |  | 27 |  |  |  |  | Low Bed Trailer | 1 | 16 | 1351.88 | 21630.08
6 |  |  |  | 28 |  |  |  |  | Backhoe (0.80 cu.m.) | 1 | 16 | 1537 | 24592
7 |  |  |  | 29 |  |  |  |  | Crawler Crane (36-40T) | 1 | 16 | 1902 | 30432
8 |  |  |  | 30 |  |  |  |  | Payloader (1.50 cu.m.) | 1 | 16 | 1733 | 27728
9 |  |  |  | 31 |  |  |  |  | Dump Truck (12 cu.m. yd.) | 1 | 16 | 1420 | 22720
10 |  |  |  | 32
11 |  |  |  | 33 |  |  |  | 1 | One Bagger Mixer | 2 | 1 | 1420
12 |  |  |  | 34 |  |  |  | 1 | Concrete Vibrator | 1 | 1 | 1537 | 1537
13 |  |  |  | 35 |  |  |  |  | Water Truck (16000 L) | 1 | 0.5 | 351.5 | 175.75
14 |  |  |  | 36 |  |  |  |  | Cargo Truck (10T) | 1 | 0.15 | 1212 | 181.8
15 |  |  |  | 37 |  |  |  | 1 |  | 1 | 1 | 1902
16 |  |  |  | 38 |  |  |  | 1 |  | 1 | 1 | 2123
17 |  |  |  | 39 |  |  |  | 1 |  | 1 | 0.25 | 371 | 92.75
18 |  |  |  | 40 |  |  |  | 1 |  | 1 | 0.25 | 45.45 | 11.3625
19 |  |  |  | 41 | [5 empty] | 1 | 0.1 | 2450 | 245
20 |  |  |  | 42
21 |  |  |  | 43 |  |  |  |  | Dump Truck ( 12 cu.yd.) | 2 | 1 | 1420 | 2840
22 |  |  |  | 44 |  |  |  |  | Payloader (1.50 cu.m.) | 1 | 1 | 1733 | 1733
| SUB-TOTAL |  | 3 |  | SUB-TOTAL |  |  |  | Bulldozer (D6H SERIES II PSDS/DD) | 1 | 1 | 3379
TOTAL | [6 empty] | 3

## 6
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
DETAILED UNIT PRICE ANALYSIS (DUPA) | [12 empty] | Bituminous Concrete Surface Wearing Course,
[7 empty] | FORM-POW-2015-01D-00 |  |  | 95.1 |  |  | Stone Mastic (50 mm. thk.)
Item No./Description |  | : | Traffic Services | [6 empty] | Traffic Services | #VALUE!
Unit of Measurement |  | : | ls.
Output per hour - As Submitted |  | : | 1
Output per hour - As Evaluated |  | : | 1
A.1 | Designation |  |  | No. of Person | No. of Hours | Hourly Rate |  | Amount |  |  | 2.5
| Labor | [12 empty] | 110.1
| To be delivered at DPWH Bulacan 2nd DEO | [7 empty] | 0 | #REF! | #REF! |  |  | 61.32
| Sub-Total for A.1 - As Submitted | [7 empty] | 0
A.2 | Labor
| To be delivered at DPWH Bulacan 2nd DEO | [7 empty] | 0 | 497 | #REF!
| Sub-Total for A.2 - As Evaluated | [7 empty] | 0
B.1 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
| Sub-Total for B.1 - As Submitted | [7 empty] | 0
B.2 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
| Sub-Total for B.2 - As Evaluated | [7 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [7 empty] | 0
C.2 | Total (A.2 + B.2) - As Evaluated | [7 empty] | 0
D.1 | Output per hour - As Submitted | [7 empty] | 1
D.2 | Output per hour - As Evaluated | [7 empty] | 1
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted
E.2 | Direct Unit Cost (C.2 ÷ D.2) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Traffic Cone 30" |  |  | pc. |  |  | 1000 |  | 0
| Traffic Barrier |  |  | pc. |  |  | 3500 |  | 0
| Sub - Total for F.1 - As Submitted | [7 empty] | 0
F.2 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Traffic Cone 30" |  |  | pc. | 0 |  | 1000 |  | 0
| Traffic Barrier |  |  | pc. | 0 |  | 3500 |  | 0
| Sub - Total for F.2 - As Evaluated | [7 empty] | 0
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [7 empty] | 0
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated | [7 empty] | 0
H.1 | Overhead, Contingencies and Miscellaneous (OCM) - As Submitted | [7 empty] | 0 | 0% | 0
H.2 | Overhead, Contingencies and Miscellaneous (OCM) - As Evaluated | [7 empty] | 0
I.1 | Contractor's Profit (CP) - As Submitted | [7 empty] | 0 | 0% | 0
I.2 | Contractor's Profit (CP) - As Evaluated | [7 empty] | 0
J.1 | Value Added Tax (VAT) - As Submitted | [5 empty] | 5% |  | 0
J.2 | Value Added Tax (VAT) - As Evaluated | [5 empty] | 5% |  | 0
K.1 | Total Unit Cost - As Submitted | [7 empty] | 0
K.2 | Total Unit Cost - As Evaluated | [7 empty] | 0
Prepared By : |  |  |  |  | Checked/Reviewed By :
| JAN ARVIN H. CRUZ |  |  |  | EDGAR Y. NICDAO
| Engineer II |  |  |  |  | Engineer II
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
DETAILED UNIT PRICE ANALYSIS (DUPA) | [12 empty] | Bituminous Concrete Surface Wearing Course,
[7 empty] | FORM-POW-2015-01D-00 |  |  | 95.1 |  |  | Stone Mastic (50 mm. thk.)
Item No./Description |  | : | Handtools and Safety Gears | [6 empty] | Handtools and Safety Gears | #VALUE!
Unit of Measurement |  | : | l.s.
Output per hour - As Submitted |  | : | 1
Output per hour - As Evaluated |  | : | 1
A.1 | Designation |  |  | No. of Person | No. of Hours | Hourly Rate |  | Amount |  |  | 2.5
| Labor | [12 empty] | 110.1
| To be delivered at DPWH Bulacan 2nd DEO | [7 empty] | 0 | #REF! | #REF! |  |  | 61.32
0
[9 empty] | 0 | #REF!
[10 empty] | #REF! |  |  | 75.1
| Sub-Total for A.1 - As Submitted | [7 empty] | 0
A.2 | Labor
| To be delivered at DPWH Bulacan 2nd DEO | [7 empty] | 0 | 497 | #REF!
0
[9 empty] | 0 | #REF!
[10 empty] | #REF! |  |  | 75.1
| Sub-Total for A.2 - As Evaluated | [7 empty] | 0
B.1 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
0
0
0
0
| Sub-Total for B.1 - As Submitted | [7 empty] | 0
B.2 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
0
0
0
0
| Sub-Total for B.2 - As Evaluated | [7 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [7 empty] | 0
C.2 | Total (A.2 + B.2) - As Evaluated | [7 empty] | 0
D.1 | Output per hour - As Submitted | [7 empty] | 1
D.2 | Output per hour - As Evaluated | [7 empty] | 1
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted
E.2 | Direct Unit Cost (C.2 ÷ D.2) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Buggy |  |  | pc. | 45 |  | 5300 |  | 238500 | 5182
| Grasscutter with Accessories |  |  | pc. | 10 |  | 20000 |  | 200000
| Boots |  |  | pc. | 60 |  | 345 |  | 20700
| Shovel |  |  | pc. | 330 |  | 384 |  | 126720
| Scrapper |  |  | pc. | 100 |  | 50 |  | 5000
| Halabas |  |  | pc. | 200 |  | 384 |  | 76800
| Bolo |  |  | pc. | 100 |  | 750 |  | 75000
| Axe (Small) |  |  | pc. | 100 |  | 470 |  | 47000
| Walk Meter |  |  | pc. | 50 |  | 6500 |  | 325000
| Measuring Tape |  |  | pc. | 150 |  | 800 |  | 120000 | 2479377.6
| Rake |  |  | pc. | 200 |  | 250 |  | 50000
| Caps |  |  | pc. | 100 |  | 350 |  | 35000
| Longsleeve with DPWH Logo |  |  | pc. | 350 |  | 300 |  | 105000
| Traffic Vest |  |  | pc. | 350 |  | 300 |  | 105000
| Safety Floves |  |  | pc. | 350 |  | 380 |  | 133000
| Burner #5 |  |  | pc. | 50 |  | 2000 |  | 100000
| Sub - Total for F.1 - As Submitted | [7 empty] | 1762720
F.2 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Buggy |  |  | pc. | 45 |  | 5300 |  | 238500
| Grasscutter with Accessories |  |  | pc. | 10 |  | 20000 |  | 200000
| Boots |  |  | pc. | 60 |  | 345 |  | 20700
| Shovel |  |  | pc. | 330 |  | 384 |  | 126720
| Scrapper |  |  | pc. | 100 |  | 50 |  | 5000
| Halabas |  |  | pc. | 200 |  | 384 |  | 76800
| Bolo |  |  | pc. | 100 |  | 750 |  | 75000
| Axe (Small) |  |  | pc. | 100 |  | 470 |  | 47000
| Walk Meter |  |  | pc. | 50 |  | 6500 |  | 325000
| Measuring Tape |  |  | pc. | 150 |  | 800 |  | 120000
| Rake |  |  | pc. | 200 |  | 250 |  | 50000
| Caps |  |  | pc. | 100 |  | 350 |  | 35000
| Longsleeve with DPWH Logo |  |  | pc. | 350 |  | 300 |  | 105000
| Traffic Vest |  |  | pc. | 350 |  | 300 |  | 105000
| Safety Floves |  |  | pc. | 350 |  | 380 |  | 133000
| Burner #5 |  |  | pc. | 50 |  | 2000 |  | 100000
| Sub - Total for F.2 - As Evaluated | [7 empty] | 1762720
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [7 empty] | 1762720
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated | [7 empty] | 1762720
H.1 | Overhead, Contingencies and Miscellaneous (OCM) - As Submitted | [7 empty] | 0 | 0% | 0
H.2 | Overhead, Contingencies and Miscellaneous (OCM) - As Evaluated | [7 empty] | 0
I.1 | Contractor's Profit (CP) - As Submitted | [7 empty] | 0 | 0% | 0
I.2 | Contractor's Profit (CP) - As Evaluated | [7 empty] | 0
J.1 | Value Added Tax (VAT) - As Submitted | [5 empty] | 5% |  | 88136
J.2 | Value Added Tax (VAT) - As Evaluated | [5 empty] | 5% |  | 88136
K.1 | Total Unit Cost - As Submitted | [7 empty] | 1850856
K.2 | Total Unit Cost - As Evaluated | [7 empty] | 1850856
Prepared By : |  |  |  |  | Checked/Reviewed By :
| JAN ARVIN H. CRUZ |  |  |  | EDGAR Y. NICDAO
| Engineer II |  |  |  |  | Engineer II
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
DETAILED UNIT PRICE ANALYSIS (DUPA) | [12 empty] | Bituminous Concrete Surface Wearing Course,
[7 empty] | FORM-POW-2015-01D-00 |  |  | 95.1 |  |  | Stone Mastic (50 mm. thk.)
Item No./Description |  | : | Asphalt Plant Mix Hot (Furnished) | [6 empty] | Asphalt Plant Mix Hot (Furnished) | #VALUE!
Unit of Measurement |  | : | mt.
Output per hour - As Submitted |  | : | 1
Output per hour - As Evaluated |  | : | 1
A.1 | Designation |  |  | No. of Person | No. of Hours | Hourly Rate |  | Amount |  |  | 2.5
| Labor | [12 empty] | 110.1
| To be delivered at DPWH Bulacan 2nd DEO | [7 empty] | 0 | #REF! | #REF! |  |  | 61.32
0
[9 empty] | 0 | #REF!
[10 empty] | #REF! |  |  | 75.1
| Sub-Total for A.1 - As Submitted | [7 empty] | 0
A.2 | Labor
| To be delivered at DPWH Bulacan 2nd DEO | [7 empty] | 0 | 497 | #REF!
0
[9 empty] | 0 | #REF!
[10 empty] | #REF! |  |  | 75.1
| Sub-Total for A.2 - As Evaluated | [7 empty] | 0
B.1 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
0
0
0
0
| Sub-Total for B.1 - As Submitted | [7 empty] | 0
B.2 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
0
0
0
0
| Sub-Total for B.2 - As Evaluated | [7 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [7 empty] | 0
C.2 | Total (A.2 + B.2) - As Evaluated | [7 empty] | 0
D.1 | Output per hour - As Submitted | [7 empty] | 1
D.2 | Output per hour - As Evaluated | [7 empty] | 1
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted
E.2 | Direct Unit Cost (C.2 ÷ D.2) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Bituminous Concrete Surface with Asphalt |  |  | m.t. | 52.32 |  | 9100 |  | 476112 | 5182
Plant Mix Hot (Furnished)
| Sub - Total for F.1 - As Submitted | [7 empty] | 476112
F.2 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Bituminous Concrete Surface with Asphalt |  |  | m.t. | 52.32 |  | 9100 |  | 476112
Plant Mix Hot (Furnished)
| Sub - Total for F.2 - As Evaluated | [7 empty] | 476112
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [7 empty] | 476112
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated | [7 empty] | 476112
H.1 | Overhead, Contingencies and Miscellaneous (OCM) - As Submitted | [7 empty] | 0 | 0% | 0
H.2 | Overhead, Contingencies and Miscellaneous (OCM) - As Evaluated | [7 empty] | 0
I.1 | Contractor's Profit (CP) - As Submitted | [7 empty] | 0 | 0% | 0
I.2 | Contractor's Profit (CP) - As Evaluated | [7 empty] | 0
J.1 | Value Added Tax (VAT) - As Submitted | [5 empty] | 5% |  | 23805.6
J.2 | Value Added Tax (VAT) - As Evaluated | [5 empty] | 5% |  | 23805.6
K.1 | Total Unit Cost - As Submitted | [7 empty] | 499917.6
K.2 | Total Unit Cost - As Evaluated | [7 empty] | 499917.6
Prepared By : |  |  |  |  | Checked/Reviewed By :
| JAN ARVIN H. CRUZ |  |  |  | EDGAR Y. NICDAO
| Engineer II |  |  |  |  | Engineer II
Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
0
DETAILED UNIT PRICE ANALYSIS (DUPA)
FORM-POW-2015-01D-00
Item No./Description |  | : | Traffic Services
Unit of Measurement |  | : | ls.
Output per hour - As Submitted |  | : | 1
Output per hour - As Evaluated |  | : | 1
A.1 | Designation |  |  | No. of Person | No. of Hours | Hourly Rate |  | Amount
Labor
0
| Sub-Total for A.1 - As Submitted | [7 empty] | 0
A.2 | Labor
0
| Sub-Total for A.2 - As Evaluated | [7 empty] | 0
B.1 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
| Sub-Total for B.1 - As Submitted | [7 empty] | 0
B.2 | Name and Capacity |  |  | No. of Units | No. of Hours | Hourly Rate |  | Amount
Equipment
0
| Sub-Total for B.2 - As Evaluated | [7 empty] | 0
C.1 | Total (A.1 + B.1) - As Submitted | [7 empty] | 0
C.2 | Total (A.2 + B.2) - As Evaluated | [7 empty] | 0
D.1 | Output per hour - As Submitted | [7 empty] | 171
D.2 | Output per hour - As Evaluated | [7 empty] | 171
E.1 | Direct Unit Cost (C.1 ÷ D.1) - As Submitted
E.2 | Direct Unit Cost (C.2 ÷ D.2) - As Evaluated
F.1 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount |  | 0 | 7380.9524
| Materials | [8 empty] | 20822.8571
| Plastic Barrier with LED Illuminated Directional Indicators:COLOR: YELLOW FINISH:Amber Light Action:Flashing, Trailing Reflective, Solar Battery, Rechargeable LifePo4,3000maH,3.2V. |  |  | ea. |  |  |  |  | 0 | 270 | 15 | 18
| Traffic Cone:Length - 360mm, width - 360mm,height - 940mm: Yellow Illuminated : Flashing reflective:Rechargeable Life |  |  | ea. |  |  |  |  | 0 | 928 | 16 | 58
| Concrete Barrier with LED Illuminated Directional Indicators:COLOR: YELLOW FINISH:Amber Light Action:Flashing, Trailing Reflective, Solar Battery, Rechargeable LifePo4,3000maH,3.2V. |  |  | ea. | 108 |  | 21864 |  | 2361312
| Sub - Total for F.1 - As Submitted | [7 empty] | 2361312
F.2 | Name and Specification |  |  | Unit | Quantity | Unit Cost |  | Amount
Materials
| Plastic Barrier with LED Illuminated Directional Indicators:COLOR: YELLOW FINISH:Amber Light Action:Flashing, Trailing Reflective, Solar Battery, Rechargeable LifePo4,3000maH,3.2V. |  |  | ea. | 0 |  | 0 |  | 0
| Traffic Cone:Length - 360mm, width - 360mm,height - 940mm: Yellow Illuminated : Flashing reflective:Rechargeable Life |  |  | ea. | 0 |  | 0 |  | 0
| Concrete Barrier with LED Illuminated Directional Indicators:COLOR: YELLOW FINISH:Amber Light Action:Flashing, Trailing Reflective, Solar Battery, Rechargeable LifePo4,3000maH,3.2V. |  |  | ea. | 108 |  | 21864 |  | 2361312
| Sub - Total for F.2 - As Evaluated | [7 empty] | 2361312
G.1 | Direct Unit Cost (E.1 + F.1) - As Submitted | [7 empty] | 2361312
G.2 | Direct Unit Cost (E.2 + F.2) - As Evaluated | [7 empty] | 2361312
H.1 | Overhead, Contingencies and Miscellaneous (OCM) - As Submitted | [7 empty] | 0
H.2 | Overhead, Contingencies and Miscellaneous (OCM) - As Evaluated | [7 empty] | 0
I.1 | Contractor's Profit (CP) - As Submitted | [7 empty] | 0
I.2 | Contractor's Profit (CP) - As Evaluated | [7 empty] | 0
J.1 | Value Added Tax (VAT) - As Submitted | [5 empty] | 5% |  | 118065.6
J.2 | Value Added Tax (VAT) - As Evaluated | [5 empty] | 5% |  | 118065.6
K.1 | Total Unit Cost - As Submitted | [7 empty] | 2479377.6
K.2 | Total Unit Cost - As Evaluated | [7 empty] | 2479377.6
Prepared By : |  |  |  |  | Checked/Reviewed By :
| JAN ARVIN H. CRUZ |  |  |  | EDGAR Y. NICDAO
| Engineer II |  |  |  |  | Engineer II

## edit title, location, here
Republic of the Philippines
DEPARTMENT OF PUBLIC WORKS AND HIGHWAYS
Region III
Bulacan Second District Engineering Office
Sta. Maria, Bulacan
PROGRAM OF WORK / BUDGET COST FOR | [8 empty] | 55 | 53+-77
PUBLIC WORKS AND HIGHWAYS PROJECT
Name of Project : |  |  | Roadbed/Embankment Width : |  |  |  |  | 54000
|  |  | Pavement Width : |  |  |  |  | 52935 | a.) K0021+(-045) - K0022+760 with exceptions
1065
60078
Location : |  |  | Bridge/Structure : |  |  |  |  | 58579
Project No. |  |  | Type of Substructure |  |  |  |  | 1499
Appropriation : | 500000 |  | Type of Superstructure |  |  |  |  | 2564 | 909.95 |  | 2.7
Source of Fund : | For Funding |  | No. of Span/Storey :
Classification : | National Roads |  | No. of Piers : | [5 empty] | 60.3
Limits : |  |  | Starting Date : Upon Approval | [6 empty] | 2.7 | 836.4
Net Length : |  |  | No. of Days to be completed : |  |  | 81 calendar days
DESCRIPTION OF WORK TO BE DONE |  | % OF | EQUIPMENTS
|  |  | DESCRIPTION |  |  | NEEDED | AVAILABLE |  |  | a. Dump Truck (10 cu.m.) |  | a. Crawler Crane ( 36 - 40 T )
PART B - OTHER GENERAL REQUIREMENTS |  |  | Stake Truck (5 T) |  |  | 1 | 1 |  | Dump Truck (10 cu.m.) |  |  | b. Vibro Hammer (Hydraulic Operated)
PART E - SURFACE COURSES |  |  | Barricade Flasher Light (3V, Battery Operated, Amber Color, with lifespan consideration of 6 months) |  |  | 4 | 4 |  | Backhoe (0.80 cu.m.) |  |  | c. Welding Machine (Gas Operated)
PART H - MISCELLANEOUS STRUCTURES | [8 empty] | Bar Cutter |  |  | d. Cutting Outfit
612 (1) | [8 empty] | Bar Bender |  |  |  |  | #REF!
|  |  | Cargo/Service Truck (10T, 270 Hp) |  |  | 1 | 1 |  | Cargo Truck (10 T, 270 Hp) |  |  |  |  | #REF!
|  |  | Backhoe (0.80 cu.m), SE 130 LC-2 |  |  | 1 | 1 |  | One Bagger Mixer |  |  |  |  | #REF!
|  |  | Motorized Road Grader (140hp), G710A |  |  | 1 | 1 |  | Concrete Vibrator |  |  |  |  | #REF!
|  |  | Vibratory Roller (10 m.t.), SD100DC |  |  | 1 | 1 |  | Water Truck (1000 gal.)
|  |  | Water Truck (16000L) |  |  | 1 | 1 |  | Crawler Crane ( 36 - 40 T )
|  |  | Asphalt Distributor, 10ft. Wide (5 tons) |  |  | 1 | 1 |  | Vibro Hammer (Hydraulic Operated) |  |  |  | 3
|  |  | Power Broom (2 m. wide) |  |  | 1 | 1 |  | Welding Machine (Gas Operated) | [6 empty] | 897.6 |  | 2.249
|  |  | Asphalt Paver (80 Hp), NF220BIIVDM |  |  | 1 | 1
|  |  | Pneumatic Tire Roller (10 m.t.) |  |  | 1 | 1
|  |  | Tandem Steel Roller (10.1 m.t.), CC421 |  |  | 1 | 1 |  |  |  |  | 52723 | 56273 | 59823
ESTIMATED COST OF PROPOSED WORK | [10 empty] | 3171.825 |  |  |  | #REF!
[9 empty] | #REF! | #REF!
[6 empty] | DIRECT COST |  |  |  | 2.7 | 0 | 13.4
ITEM NO. | D E S C R I P T I O N |  | UNIT | QUANTITY |  |  |  |  | 6.35 | 11.1667 | 0
[6 empty] | UNIT COST | TOTAL COST |  | #REF! |  | 0 |  | #REF!
PART B | OTHER GENERAL REQUIREMENTS | [8 empty] | 10.5833 | 0 | 4.35 |  | 500000
B.5 | Project Billboard/ Signboard |  | each |  | 3 | #REF! | #REF! |  | 6.9333 |  |  | 5.4375
B.7 | Occupational Safety and Health Program |  | month |  | 3 | #REF! | #REF! |  | 5.53 | 6.9333 | #REF!
B.8 | Traffic Management |  | month |  | 3 | #REF! | #REF! |  | 2500000 |  | #REF! | 2.7 |  |  |  |  | #REF!
B.9 | Mobilization/Demobilization |  | l.s. |  | 1 | #REF! | #REF! |  | 0 | [7 empty] | #REF!
PART C | EARTHWORKS | [7 empty] | 0 | #REF! | 0
201 (1) | Aggregate Base Course |  | cu.m. |  |  | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF!
PART E | MISCELLANEOUS | [7 empty] | #REF! | #REF! | #REF!
| Traffic Services |  | ls. |  | 1 | 2479377.6 | 2479377.6
| Traffic Services |  | ls. |  | 1 | 0 | 0
| Bituminous Tack Coat RC-Cut-Back Asphalt (Grade70) | [5 empty] | 0
| MC Cut Back Asphalt | [5 empty] | 0
| Repainting of Road Sections | [5 empty] | 0 |  | 20622.4 |  | #REF! | #REF! | 0 | #REF!
| Handtools and Safety Gears | [5 empty] | 0 |  |  | #REF! | 21.7499 | 0 | 11.06 | 0 |  | 21.7499
BREAKDOWN OF ESTIMATED | [8 empty] | #REF! |  |  | #REF! |  | #REF!
EXPENDITURES
1. Labor ____ | Mandays : |  | a. Direct Cost Sub-Total |  |  |  | 2479377.6 |  |  | #REF! | #REF! | #REF!
2. Materials ____________ : |  |  | b. Construction Engineering ( 2.0%) | [5 empty] | 3.5% |  |  | 2080
3. Rental of Equipment ___ : |  |  | c. Escalation Contingency |  |  |  |  | #REF! |  |  |  | 1.9
4. Quality Control ________: |  |  |  | 12% PA % |  |  |  |  | 80.84 | 6.3 | #REF! | #REF!
5. O.C.M. ______________: |  |  | d. Acquisition of Publication | [5 empty] | 80.84 | 6.3 | #REF! | #REF!
6. Profit & Tax __________: |  |  | e. Total Estimated Cost |  |  | P | 2479377.6 |  | 80.84
7. Engineering __________ : |  |  |  |  | S A Y = | P | 2500000 |  | 20622.4 |  |  | #REF!
8. Mobilization : | [8 empty] | #REF! | main bar/splicing |  | 1000000
PREPARED BY : |  | CHECKED BY : |  |  |  | SUBMITTED BY : |  |  | #REF! | 12.6 |  | #REF!
#REF!
EDUARDO S. NEPOMUCENO |  | RONNEL BRYAN A. DE LEON |  |  |  | EDGARDO C. PIÑGOL |  |  | 100.01 | 99.99 | 202 | 45 |  | 3.3
Const. Maint. Foreman |  | Engineer II |  |  |  | Chief, Maintenance Section |  |  |  | 647 | 420 | 93.5644 |  | 39.0555
| RECOMMENDING APPROVAL : |  |  |  | APPROVED : |  |  |  | #REF! |  |  |  |  | 16.5
| GENE S. LEAÑO |  |  |  | GEORGE DC. SANTOS | [8 empty] | 1.1
| Assistant District Engineer |  |  |  | District Engineer | [8 empty] | 5.5
1482.5
8895
.
SUBMITTED BY : REVIEWED BY (AS TO UNIT COST): |  |  |  |  | REVIEWED BY (AS TO QUANTITY): |  |  |  | RECOMMENDED BY : |  |  |  | APPROVED BY :
| RAMIRO M. CRUZ | JESUS O. OBORDO |  |  | ARTHUR Q. SANTOS |  |  |  | LORETA M. MALALUAN |  |  |  | ANTONIO V. MOLANO, JR. CESO III
| District Engineer | Chief, Construction Division |  |  | Chief, Planning & Design Division |  |  |  | Acting Director III |  |  |  |  | Director IV

## PR
Appendix 60
Republic of the Philippines
DEPARTMENT OF PUBLIC WORKS AND HIGHWAYS
BULACAN 2ND DISTRICT ENGINEERING OFFICE
Sta. Maria, Bulacan, Region III
PURCHASE REQUEST
Entity Name: | DPWH - Bulacan 2nd District Engineering Office |  |  | Fund Cluster: __________________
Office/Section : |  | PR No.: |  | Date: | May 21,2025
MAINTENANCE |  | Responsibility Center Code : _________
Stock/ Property No. | Unit | Item Description | Quantity | Unit Cost | Total Cost
1.05
| ea. | Plastic Barrier with LED Illuminated Directional Indicators:COLOR: YELLOW FINISH:Amber Light Action:Flashing, Trailing Reflective, Solar Battery, Rechargeable LifePo4,3000maH,3.2V. | 0 | 0 | 0 | 0
| ea. | Traffic Cone:Length - 360mm, width - 360mm,height - 940mm: Yellow Illuminated : Flashing reflective:Rechargeable Life | 0 | 0 | 0 | 0
| ea. | Concrete Barrier with LED Illuminated Directional Indicators:COLOR: YELLOW FINISH:Amber Light Action:Flashing, Trailing Reflective, Solar Battery, Rechargeable LifePo4,3000maH,3.2V. | 108 | 22957.2 | 2479377.6 | 21864
0
0
0
0
|  |  |  | TOTAL | 2479377.6
Purpose: | Procurement of Materials for use in Traffic Services along Manila North Road Critical Section
| Requested by: |  | Approved by:
Signature :
Printed Name : | ARNEL C. GUBALLA |  |  | GEORGE DC. SANTOS
Designation : | Chief, Maintenance Section |  |  | District Engineer